## Slide 1: GLAMSPACE: YOUR BEAUTY HUB
PRESENTED BY : LAVENDA ALELA
COURSE : DBIT KCA UNIVERSITY
DATE : 6/02/2025

## Slide 2: BACKGROUND
Glamspace: your beauty hub is a solon and barber shops locator. The system will specialize in salon and barber shop locating, pricing solutions, and beauty services. With a strong commitment to efficiency and customer satisfaction, the system serves a diverse clientele, including entrepreneurs, office workers ,students and anyone interested in beauty services.
Growing beauty and grooming industry
Increasing demand for convenient service location
Digital transformation in beauty sector
Rise of mobile and web-based solutions

## Slide 3: PROBLEM STATEMENT
Consumers often face significant challenges in locating nearby
salons or barbershops due to the lack of a centralized
information system. This results in limited access to essential
service details and pricing, making it difficult to compare
different service providers effectively. Additionally, the absence
of a reliable review system leaves users without trustworthy
feedback on the quality of services, leading to a time-
consuming and inefficient process of physically searching
for suitable locations. Consequently, these issues collectively
hinder the overall experience of finding and utilizing salon
or barbershop services.

## Slide 4: PROPOSED SOLUTION
The proposed solution is to have a system equipped with locator where one can find salon and grooming services easily.
Digital locator system using:
• Visual Basic .NET
• Microsoft Access Database
• User-friendly interface
Features:
• Location-based search
• Service and price comparison
• Review and rating system
• Detailed shop information

## Slide 5: PROJECT OBJECTIVES
Feasibility Study:
Technical feasibility; hardware, software and skills
Economic feasibility; development and operation cost
Operational feasibility; user acceptance
Analysis:
Requirements gathering; using interviews, surveys
System analysis; current system evaluation
User needs assessment
Design:
Database design; tables
Interface design; search screen
System architecture
Testing:
Unit testing; testing individual components
Integration testing; testing combined components
User acceptance testing; real user testing
Implementation:
System deployment; database setup
User training; training sessions
Maintenance plan; regular updates

## Slide 6: PROJECT SCOPE
In Scope:
Salon/Barbershop registration
Search functionality
Review system
Basic reporting
Location mapping
Out of Scope:
Online booking
Payment processing
Real-time chat
Mobile application

## Slide 7: PROJECT JUSTIFICATION
In today's fast-paced world, convenience and efficiency are paramount, and this extends to personal grooming services. The Salon and Barber Shop Locator project is justified by several compelling factors that address current market needs and consumer pain points.
Difficulty in Finding Nearby Salons/Barbershops
Lack of Centralized Information System
Limited Access to Service Details and Pricing
Time Wasted in Physical Location Search
Inefficient Comparison of Service Providers

## Slide 8: LITERATURE REVIEW
The beauty and personal care market is experiencing significant growth, driven by consumer preferences and technological advancements (Johnson, M. A., & Smith, K. B. 2023). Statista highlights the rising demand for natural and organic products, while IBISWorld examines the US hair and nail salon market, emphasizing demographic and economic influences. Johnson and Smith discuss the benefits and challenges of location-based service (LBS) applications, which enhance convenience and offer personalized recommendations. Thompson and Wilson's development of a salon finder system using Visual Basic addresses the difficulty of locating nearby salons, showcasing its practical application and positive user feedback. Overall, the literature underscores the industry's efforts to improve accessibility and convenience through technological solutions.

## Slide 9: DEVELOPMENT METHODOLOGY
AGILE METHODOLOGY
Sprints:
Planning and Requirements
Database Design
UI Development
Core Features
Testing and Review
Deployment
Benefits:
Flexible development
Regular feedback
Quick iterations
Risk management

## Slide 10: PROJECT RESOURCES
Hardware:
Computer system
Database server
Development machine
Software:
Visual Studio
Microsoft Access
Testing tools
Human Resources:
Developer
Tester
Project supervisor

## Slide 11: PROJECT BUDGET
Development Costs:
Software licenses; $200
Hardware requirements; $0
Development time; $0
Testing resources; $100
Documentation; $50
Operational Costs:
Maintenance; $100
Updates; $50
Training; $150

## Slide 12: PROJECT SCHEDULE
WEEK4 | DAYS | PHASE | TASK | DELIVERABLE
Week 1 | 1-5 | Project planning | Requirement gathering, project scope definition | Project plan document
Week 2 | 6-10 | Analysis phase | User requirement analysis, system requirement | Requirement documentation
Week 3 | 11-15 | Database design | Database design, table relationships | Database design document
Week 4 | 16-20 | User interface design | UI mockups interface design | UI design prototype

## Slide 13: conti
WEEKS | DAYS | PHASE | TASKS | DELIVERABLES
Week 5-6 | 21-30 | Core development | Core functionality coding, database implementation | Basic working system
Week 7 | 31-35 | Feature development | Search functionality | Complete system features
Week 8 | 36-40 | Testing phase | Unit testing, Bug fixing | Test results document
Week 9 | 41-45 | System integration and testing | User acceptance testing final adjustments | Test completion report
Week 10 | 46-50 | Deployment and documentation | System deployment, project handover | Final system and documentation

## Slide 14: PROJECT GANTT CHART
Visual Gantt chart showing:
Tasks
Duration
Dependencies
Milestones
Resources

## Slide 15: PROJECT RISKS AND MITIGATION
RISKS AND MITIGATION
Technical Risks:
Database performance challenges
System compatibility
Data insecurity
Mitigation Strategies:
Regular testing
Backup systems
Security protocols
Contingency planning

## Slide 16: CONCLUSION
The Salon and Barbershop Locator System represents a significant advancement in connecting beauty service providers with potential customers. Through the implementation of Visual Basic .NET and Microsoft Access, this system offers a robust solution to the current challenges in locating and evaluating beauty services.
The Salon and Barbershop Locator System represents a practical and effective solution to real-world challenges in the beauty service industry. By bridging the gap between service providers and customers, this system not only solves current problems but also lays the foundation for future technological integration in the beauty service sector. The successful implementation of this project will contribute significantly to the modernization of beauty service discovery and evaluation processes.

## Slide 17: REFRENCES
Statista Research Department. (2024). Beauty & personal care market - Statistics & facts. Statista. Retrieved from https://www.statista.com/topics/4503/beauty-and-personal-care-market/
IBISWorld. (2023). Hair & nail salons in the US - Market size 2005–2024. Industry Report 81211. Retrieved from https://www.ibisworld.com/industry-statistics/market-size/hair-nail-salons-united-states/
Johnson, M. A., & Smith, K. B. (2023). Location-based service applications in the beauty industry: A systematic review. Journal of Information Systems, 45(2), 112-128.
Thompson, R., & Wilson, J. (2022). Development of a salon finder system using Visual Basic: